## Schedule
Plan |  |  | Task |  |  |  | Actual
Month | Date | Weekday | Subject | Item | Detail | Note | HungNQ | NhoNT | Dang | VinhNT | LinhNK | ThuongLT
1 | 1 | Mon
| 2 | Tue | HTML Mass Production KT & Hands-on | Hands-on | Update exercise | Team udpdate exercise by practice from Mr. Nghia --> All Source code Ref: http://192.168.20.40/svn/17E276/99_Others/DN.KT.Hands-on.Materials/Exercise_result | Done | Done |  | Done | Done | Done
| 3 | Wed | Prepare Environment | Prepare Environment for project | Get source code and check App run nomaly |  | Done | Done |  |  | Done | Done
| 4 |  |  | Setup Plugin | Follow README.md Setup and check how to use Plugin |  | Done | Done |  |  | Done | Done
| 5 | Thu | Angular Cli | Basic | Internet Investigate | About Angular Cli. Why we use Angular Cli for project https://github.com/angular/angular-cli/wiki https://github.com/angular/angular-cli/wiki/generate https://nrwl.io/nx (動画もみてください) https://nrwl.io/nx/overview https://nrwl.io/nx/why-a-workspace https://nrwl.io/nx/guide-getting-started https://nrwl.io/nx/guide-nx-workspace https://nrwl.io/nx/guide-setting-up-ngrx https://nrwl.io/nx/guide-data-persistence --> ThuongLT rearch and Sharing for all team | [5 empty] | Done
[5 empty] | Meeting sharing | Meeting sharing about NRWL | Done | Done |  |  | Done | Done
[5 empty] | More Detail on Internet | Some command + parameter which is necessary for Project | Done | Done |  |  | Done | Done
| 6 | Thu | Angular/ngrx | Advance | Research about Rxjs,Redux and ngrx | 1. Redux: How to implement application with Redux. 2. Using Redux and Observable 3. Using ngrx implement simple application -> LinhNK & NhoNT research and sharing to all member |  | Done |  |  | Done
| 6 | Thu | Application Settings: to know overall structure | Understand Project Structure | Understand Project Structure | Make development environment: to know project structure https://bitbucket.org/4digit-developers/999-999-fr-spl/wiki/training-2#markdown-header-make-development-environment-to-know-project-structure Explain each Folder/file.xxx in project --> HungNQ check and sharing to all member | Done
| 5 | Fri | Angular/ngrx | Advance | Meeting sharing | LinhNK & NhoNT sharing knowledge to all member | Done | Done |  |  | Done | Done
| 5 | Fri | Application Settings: to know overall structure | Understand Project Structure | Meeting sharing | HungNQ sharing knowledge to all member | Done | Done |  |  | Done | Done
| 6 | Sat
| 7 | Sun
| 8 | Mon | Make sapmle | Prepare Environment | Get source code from branch dev/master -Make a app using @nrwl/nx code generator | -Make a app using @nrwl/nx code generator -Setting app.module -Check app Training run normally | Done | Done |  |  | Done | Done
|  |  |  | Read requirement dummy user flow | -Read and confirm requirement | https://bitbucket.org/4digit-developers/999-999-fr-spl/wiki/training-2#markdown-header-make-dummy-user-flow-to-know-how-to-make-screens-logics | Done | Done |  |  | Done | Done
| 9 | Tue |  | Coding sample | 1. Make dummy json as dummy API using @angular/in-memory-web-api 2.Create Module 3. Setting Routing 4. Created scrren Load list and Load Api from #1
| 10 | Wed |  | Coding sample | 5. Write edit screen using data from API 6.Write data update process using ngrx 7. Test and review all member
| 11 | Thu
| 12 | Fri
| 13 | Sat
| 14 | Sun
| 15 | Mon
| 16 | Tue
| 17 | Wed
| 18 | Thu
| 19 | Fri
| 20 | Sat
| 21 | Sun
| 22 | Mon
| 23 | Tue
| 24 | Wed
| 25 | Thu
| 26 | Fri
| 27 | Sat
| 28 | Sun
| 29 | Mon
| 30 | Tue
| 31 | Wed
案件に入るため、12月からトレーニング実施しない